## Pair
Story# | Feature | Priority | Story title | In order to | As a | I should be able to | Acceptance criteria | Local tests (Unit & Local Integration) | Functional tests (Full Integration & E2E) | Sprint# | Status
A001 | cases | M | View my cases | manage my cases | case manager | view all my cases | 1. can view list of own cases alphabetically | LA001-01: should list own cases in card view by default LA001-02: should list cases alphabetically LA001-03: should navigate to case activities when clicked on a case LA001-04: should limit case display name to 20 characters with tooltip and expandable view LA001-05: should reactively add or remove case assignments from list LA001-06: should be able to switch view mode between card view, tabular view or bucket view LA001-07: should allow option to retain last view mode selection | FA001-01: should list own cases FA001-02: should reactively add or remove case assignments from list FA001-03: should retain last view mode selection within a session FA001-003-04: should list selected case activities when clicked on a case
A002 | cases | M | Add a case | track activities of a new case | case manager | add a new case | 1. can add my new cases 2. cannot use invalid names for cases | LA002-01: should show option to "Add new case" LA002-02: should show new form when "Create" button clicked LA002-03: should not accept characters other than alphanumeric and space LA002-04: should not accept less than 5 characters or more than 50 characters LA002-05: should hide/cancel new form when Esc key pressed or cliicked outside new form. LA002-06: should not retain the last value when add cancelled and clicked again | FA002-01: should not accept duplicate case names FA002-02: should add a new case when "Create" button clicked FA003-03: should cancel add action when Esc clicked or clicked outside new form
A003 | cases | M | View my case activities | manage case activities | case manager | view my case activities | 1. can view activities of my case | LA003-01: should list case activities in tabular view by default LA003-02: should list activities based on ascending due date LA003-03: should allow option to retain last sort mode LA003-04: should open activity details pane when clicked on an activity LA001-05: should limit activity display name to 20 characters with tooltip and expandable view LA001-06: should be able to switch view mode between card view, tabular view or bucket view LA001-07: should allow option to retain last view mode selection | FA003-01: should list activities based on ascending due date FA003-02: should retain last sort mode selection within a session
A004 | cases | M | View other cases | manage cases I follow | case manager | view all cases I follow | 1. can view list of followed cases alphabetically | LA004-01: should list followed cases LA004-02: should list cases alphabetically LA004-03: should redirect to "View my case details" when clicked on a case LA004-04: should limit case display name to 20 characters with tooltip and expandable view | FA004-01: should list followed cases FA004-02: should unfollow and remove from list when case assigned to me
A005 | cases | M | View case activity details | view case updates | case manager | view my case activity details | 1. can view case activity details
A006 | cases | M | Follow a case | track other cases of interest | case manager | follow another case | 1. can view list of all other cases alphabetically 2. can follow a case from a list of other cases
A007 | cases | M | Assign a case | share work load | case manager | assign other members to a case | 1. can view list of all users 2. can assign a user to my case 3. cannot assign the same user twice to my case
A008 | Security | M | Sign in to application | perform authorized actions in the application | user | use the application only with secure credentials | 1. can sign in with the correct credentials 2. is directed into the application on successful sign in 3. User's last log in information is displayed after successful attempt 4. cannot sign in with incorrect credentials 5. All successful and failed signin attempts are logged in audit history 6. is shown a warning message on unsuccessful sign in 7. cannot login to locked or inactivated account | LA008-01: should render SignIn
A009 | Security | M | Sign in to mobile application | perform authorized actions when device is offline | mobile user | authenticate locally when the device is offline | 1. can sign in with the correct credentials when the device is offline 2. is not able to signin with incorrect credentials
A010 | Security | M | Strong password criteria | ensure the password is not easy to crack | security conscious user | only provide strong credentials to the application | 1. Password should satisfy minimum requirements 2. Last 5 paswords cannot be reused 3. User's device is registered after two factor authentication 4. User's account is locked after 5 consequtive unsuccessful attempts
A011 | Security | S | Reset password | enable access to the application when password is forgotten | user | reset my password | 1. can request forgotten username or password reset 2. User's identity is verified using two factor authentication 3. Password reset link is timed out within 24 hours
A012 | Security | M | Internal service call authentication | secure access within the application | security conscious user | secure authentication across all internal service calls within the application | 1. Application logs out automatically after 20 minutes of inactivity 2. All service calls should verify identity and authorized access of the user 3. All service calls should log invocation details in audit history 4. Any transmission of credentials should be encrypted 5. Any storage of credentials should be encrypted
A013 | Framework | M | Application layout | perform my functions | user | navigate easily to different screens and views | 1. Application displays a sidebar to navigate across modules 2. Application displays a menus to navigate across features
A014 | Framework | S | Application search | quickly visit other screens and views | user | use shortcuts for navigation | 1. Application allows a search feature to search and navigate to features
A015 | Framework | M | Context header | not have to rely on my memory and reduce possibility of errors or misinterpretation | user | see a quick view of the context information such as study, site, patient etc | 1. Application displays context details in header for the selected context 2. has ability to quickly change context from header
A016 | Framework | S | Breadcrumbs | efficiently perform my actions in the application | user | easily revisit back the screens I visited earlier to check its contents | 1. Application should display attribute based breadcrumbs 2. can click on a breadcrumb link to visit with the current context
A017 | Framework | S | Application logging |  |  | Logging
A018 | Framework | S | Display notifications |  |  | Notifications
A019 | Study Sites | M | List study participants | perform further actions for the selected participant | site team member | see a list of study participants to choose from |  | LA019-01: displays list of participants LA019-02: should display message on no results LA019-03: should display participant details LA019-04: should check for proper gender symbol LA019-05: should display count of results LA019-06: should not display horizontal scrollbar LA019-07: should display issues indicator for the participant LA019-08: should check for proper date formats LA019-09: should display total issues indicator for a participant LA019-10: should display pending enrollment date for pending enrollments LA019-11: should display loading symbol when results being fetched LA019-12: should lazy load more results on scrolling
A020 | Study Sites | M | Sort study participants listing | quickly narrow down to the participant of interest | site team member | sort the list of participants |  | LA020-01: should sort on selected criteria LA020-02: should apply selected sorting when filtering
A021 | Study Sites | M | Filter study participants listing | quickly narrow down to the participant of interest | site team member | filter the list of participants based on SPID |  | LA021-01: should filter on selected criteria LA021-02: should apply selected filtering when sorting LA021-03: should not allow invalid characters or values on filter LA021-04: show blocking message on search with no filter LA021-05: should refresh results on cancelling filter
A022 | Study Sites | M | Navigate to encounter from study participant listing | view or edit the information captured during the encounter | site team member | visit the encounter details of a selected participant |  | LA022-01: should allow to visit existing scheduled encounter for a participant LA022-02: should allow to visit existing unscheduled encounter
A023 | Enrollment | M | Register participant and create screening encounter | the participant can be screened for eligibility and subsequently enrolled for the study at the site | site team member | register a potential participant to perform screening |  | LA023-01: should allow to enroll a new participant LA023-02: should allow to create new unscheduled encounter for a participant LA023-03: should allow to create new scheduled encounter for a participant
A024 | Enrollment | M | Order lab tests | I can match the results to screening criteria | site investigating physician | order lab tests | 1. should have the ability to create, eidt or delete a lab test order 2. should have the ability to view list of test orders 3. should have option to pick labs from a dictionary list of tests. should be able to search the test based on wildcard search of test name from an autocomplete list.
A025 | Framework | M | Database and service scripts for lab tests |  | application developer | store and retrieve using a database and API services - lab results | 1. Create remote and local tables and scripts 2. Update DB model with comments 3. Create sample data and scripts 4. Create basic save and retrieval stored procedures and scripts 5. Create remote API web service & unit tests 6. Create UI / Angular data access object / service & unit tests
A026 | Enrollment | M | Add or edit lab tests | the information can be used for evaluation of the patient | site team member | add or edit the lab test results | 1. Screen displays lab tests specific to the encounter for the study selected 2. is able to add, edit or clear lab results 3. Screen defaults the test date to the encounter date. has the option to change the date to the actual test date 4. has option to add multiple results for same test on an encounter with different date times 5. Screen displays standard unit (application configured) of the test result. has option to change unit 6. Screen displays read-only standard normal ranges (application configured) for the test result. 7. has ability to identify a test result as a critical value
A027 | Enrollment | M | Lab tests additional validations | relevant results can be added productively | site team member | preconfigure settings for appropriate display of lab results | 1. Screen provides ability for skip patterns and conditional rendering of tests based on other test result values or context (gender, age etc)
A028 | Enrollment | M | Enroll participant |  | site team member | confirm the eligibility of the participant and enroll him or her into the study
A029 | Enrollment | M | Deny enrollment |  | site team member | confirm the ineligibility of the participant and decline his or her participation in the study
A030 | Enrollment | M | Edit patient registration or update screening encounter | correct any errors, complete any missing information and keep the patient record accurate | site team member | update screening encounter information
A031 | Encounters | M | Visit other encounter screens | complete the additional encounter information | site team member | add or edit additional details after participant registration | 1. should be displayed a menu to navigate across different forms of the encounter, once the encounter is recorded 2. should be able to hide or make this menu compact
A032 | Encounters | M | Add custom steps to encounters | I am able to capture any study unplanned information | site team member | add or edit additional steps to encounters | 1. should have the option to choose and add new unscheduled steps / forms on the encounter, and visit these step forms to record information, in case of scheduled or unscheduled encounters
A033 | Encounters | M | Create treatment encounters | additional information can be collected and recorded for that encounter with the patient | site team member | record the encounter information for a patient | 1. should be able to record the encounter date and type of encounter. The encounter date will default to current date. 2. should be able to reconsent the patient if required and view consent history. The patient consent date and consent version will prepopulate from enrollment. 3. In case of unscheduled visit, should record reason for visit 4. should be able to record the patient vitals at the time 5. In case of scheduled study visit, should be able to visit other forms to record additional visit information after this step 6. The encounter date, encounter type, patient consent date and consent version should be available to save the encounter. 7. should be able to save with all other empty values. For every invalid value, an issue shall be recorded. Upon valid value, any previous issue shall be cleared. 8. The system shall notify the user of successful save or error. A persistent icon on the screen will indicate presence of any issues. Clicking the icon will display all issue messages in respective fields. Clicking again will close the respective field messages.
A034 | Framework | M | Database and service scripts for treatment encounters | store the relevant information from the forms and retrieve for reports and exports | application developer | store and retrieve using a database and API services - patient vitals and encounters | 1. Create remote and local tables and scripts 2. Update DB model with comments 3. Create sample data and scripts 4. Create basic save and retrieval stored procedures and scripts 5. Create remote API web service & unit tests 6. Create UI / Angular data access object / service & unit tests
A035 | Framework | M | Database and service scripts for static encounter information tables | store the relevant information from the forms and retrieve for reports and exports | application developer | store and retrieve using a database and API services - patient demographics, co-morbidities, medication history, procedure history, physical exam, med orders and referrals | 1. Create remote and local tables and scripts 2. Update DB model with comments 3. Create sample data and scripts 4. Create basic save and retrieval stored procedures and scripts 5. Create remote API web service & unit tests 6. Create UI / Angular data access object / service & unit tests
A036 | Framework | M | Database and service scripts for dynamic encounter information tables | store the relevant information from the forms and retrieve for reports and exports | application deveboper | store and retrieve using a database and API services - dynamic form elements for eligibility, disease characteristics, social factors, risk factors, HepC history, review of systems, clinical impressions, treatment response, and discharge instructions | 1. Create remote and local tables and scripts 2. Update DB model with comments 3. Create sample data and scripts 4. Create basic save and retrieval stored procedures and scripts 5. Create remote API web service & unit tests 6. Create UI / Angular data access object / service & unit tests
A037 | Framework | M | Database and service scripts for summary and issue resolution tables | store the relevant information from the forms and retrieve for reports and exports | application developer | store and retrieve using a database and API services - encounter step summary and issue resolution information | 1. Create remote and local tables and scripts 2. Update DB model with comments 3. Create sample data and scripts 4. Create basic save and retrieval stored procedures and scripts 5. Create remote API web service & unit tests 6. Create UI / Angular data access object / service & unit tests
A038 | Enrollment | M | Add or edit patient eligibility | check criteria for eligibility during enrollment | site team member | be able to add or edit for the selected patient - patient eligibility | 1. should be able to save with atleast one nonempty values. For every invalid field value, an issue shall be recorded. Upon valid value, any previous issue for the field shall be cleared. 2. The system shall notify the user of successful save or error. A persistent icon on the screen will indicate presence of any issues. Clicking the icon will display all issue messages in respective fields. Clicking again will close the respective field messages.
A039 | Encounters | M | Add or edit patient demographics | capture and report on patient demographics during the treatment research | site team member | be able to add or edit for the selected patient - patient demographics | 1. should be able to save with atleast one nonempty values. For every invalid field value, an issue shall be recorded. Upon valid value, any previous issue for the field shall be cleared. 2. The system shall populate the current gender and date of birth from Screening information. Any update to these values should be reflected in screening and patient information. 3. The system shall notify the user of successful save or error. A persistent icon on the screen will indicate presence of any issues. Clicking the icon will display all issue messages in respective fields. Clicking again will close the respective field messages.
A040 | Encounters | M | Add or edit patient disease characteristics | capture and report on patient disease characteristics during the treatment research | site team member | be able to add or edit for the selected patient - patient disease characteristics | 1. should be able to save with atleast one nonempty values. For every invalid field value, an issue shall be recorded. Upon valid value, any previous issue for the field shall be cleared. 2. The system shall notify the user of successful save or error. A persistent icon on the screen will indicate presence of any issues. Clicking the icon will display all issue messages in respective fields. Clicking again will close the respective field messages.
A041 | Encounters | M | Add or edit patient Social factors | capture and report on patient social factors during the treatment research | site team member | be able to add or edit for the selected patient - patient social factors | 1. should be able to save with atleast one nonempty values. For every invalid field value, an issue shall be recorded. Upon valid value, any previous issue for the field shall be cleared. 2. The system shall notify the user of successful save or error. A persistent icon on the screen will indicate presence of any issues. Clicking the icon will display all issue messages in respective fields. Clicking again will close the respective field messages.
A042 | Encounters | M | Add or edit patient Risk factors | capture and report on patient risk factors during the treatment research | site team member | be able to add or edit for the selected patient - patient risk factors | 1. should be able to save with atleast one nonempty values. For every invalid field value, an issue shall be recorded. Upon valid value, any previous issue for the field shall be cleared. 2. The system shall notify the user of successful save or error. A persistent icon on the screen will indicate presence of any issues. Clicking the icon will display all issue messages in respective fields. Clicking again will close the respective field messages.
A043 | Encounters | M | Add or edit patient Hep C History | capture and report on patient Hep C History during the treatment research | site team member | be able to add or edit for the selected patient - patient Hep C History | 1. should be able to save with atleast one nonempty values. For every invalid field value, an issue shall be recorded. Upon valid value, any previous issue for the field shall be cleared. 2. The system shall notify the user of successful save or error. A persistent icon on the screen will indicate presence of any issues. Clicking the icon will display all issue messages in respective fields. Clicking again will close the respective field messages.
A044 | Encounters | M | Add or edit patient Co-morbidities | capture and report on patient co-morbidities during the treatment research | site team member | be able to add or edit for the selected patient - patient co-morbidities | 1. should be able to save with atleast one nonempty values. For every invalid field value, an issue shall be recorded. Upon valid value, any previous issue for the field shall be cleared. 2. The system shall notify the user of successful save or error. A persistent icon on the screen will indicate presence of any issues. Clicking the icon will display all issue messages in respective fields. Clicking again will close the respective field messages.
A045 | Encounters | M | Add or edit patient Medication history | capture and report on patient medication history during the treatment research | site team member | be able to add or edit for the selected patient - patient medication history | 1. should be able to save with atleast one nonempty values. For every invalid field value, an issue shall be recorded. Upon valid value, any previous issue for the field shall be cleared. 2. The system shall notify the user of successful save or error. A persistent icon on the screen will indicate presence of any issues. Clicking the icon will display all issue messages in respective fields. Clicking again will close the respective field messages.
A046 | Encounters | M | Add or edit patient Procedure history | capture and report on patient procedure history during the treatment research | site team member | be able to add or edit for the selected patient - patient procedure history | 1. should be able to save with atleast one nonempty values. For every invalid field value, an issue shall be recorded. Upon valid value, any previous issue for the field shall be cleared. 2. The system shall notify the user of successful save or error. A persistent icon on the screen will indicate presence of any issues. Clicking the icon will display all issue messages in respective fields. Clicking again will close the respective field messages.
A047 | Encounters | M | Add or edit patient Review of systems | capture and report on patient review of systems during the treatment research | site team member | be able to add or edit for the selected patient - patient review of systems | 1. should be able to save with atleast one nonempty values. For every invalid field value, an issue shall be recorded. Upon valid value, any previous issue for the field shall be cleared. 2. The system shall notify the user of successful save or error. A persistent icon on the screen will indicate presence of any issues. Clicking the icon will display all issue messages in respective fields. Clicking again will close the respective field messages.
A048 | Encounters | M | Add or edit patient Clinical Impression | capture and report on patient clinical impression during the treatment research | site team member | be able to add or edit for the selected patient - patient clinical impression | 1. should be able to save with atleast one nonempty values. For every invalid field value, an issue shall be recorded. Upon valid value, any previous issue for the field shall be cleared. 2. The system shall notify the user of successful save or error. A persistent icon on the screen will indicate presence of any issues. Clicking the icon will display all issue messages in respective fields. Clicking again will close the respective field messages.
A049 | Encounters | M | Add or edit patient Vitals | capture and report on patient vitals during the treatment research | site team member | be able to add or edit for the selected patient - patient vitals | 1. should be able to save with atleast one nonempty values. For every invalid field value, an issue shall be recorded. Upon valid value, any previous issue for the field shall be cleared. 2. The system shall notify the user of successful save or error. A persistent icon on the screen will indicate presence of any issues. Clicking the icon will display all issue messages in respective fields. Clicking again will close the respective field messages.
A050 | Encounters | M | Add or edit patient Physical Exam | capture and report on patient physical exam during the treatment research | site team member | be able to add or edit for the selected patient - patient physical exam | 1. should be able to save with atleast one nonempty values. For every invalid field value, an issue shall be recorded. Upon valid value, any previous issue for the field shall be cleared. 2. The system shall notify the user of successful save or error. A persistent icon on the screen will indicate presence of any issues. Clicking the icon will display all issue messages in respective fields. Clicking again will close the respective field messages.
A051 | Encounters | M | Add or edit patient Orders | capture and report on patient orders during the treatment research | site team member | be able to add or edit for the selected patient - patient orders | 1. should be able to save with atleast one nonempty values. For every invalid field value, an issue shall be recorded. Upon valid value, any previous issue for the field shall be cleared. 2. The system shall notify the user of successful save or error. A persistent icon on the screen will indicate presence of any issues. Clicking the icon will display all issue messages in respective fields. Clicking again will close the respective field messages.
A052 | Encounters | M | Add or edit patient Discharge Instruction | capture and report on patient discharge instruction during the treatment research | site team member | be able to add or edit for the selected patient - patient discharge instruction | 1. should be able to save with atleast one nonempty values. For every invalid field value, an issue shall be recorded. Upon valid value, any previous issue for the field shall be cleared. 2. The system shall notify the user of successful save or error. A persistent icon on the screen will indicate presence of any issues. Clicking the icon will display all issue messages in respective fields. Clicking again will close the respective field messages.
Note on J1: Vivek Pillai: Integration test cases across user stories are defined at the terminating user stories

## Features
# | Module | Feature | Area
1 |  | Preemptively apply for jobs
2 |  | Create profile of experience - Skills, testimonials, GitHub projects, Scores, customer verified feedback
3 |  | Video Profile & video Q&As
4 |  | Company asks, must haves, preferences for preemptive application including interview questionnaire & interview stats
5 |  | Company specific job application profile
6 |  | Generic job application profile
7 |  | Opt for pre-verified pool of participants
8 |  | Third party screening
9 |  | Third party provider - reputation management
10 |  | Prospective employees run background check on themselves - transparentme
11 |  | Acertiv - external certification
12 |  | Proofsheet concept - Verify claims from supervisors and customers
13 |  | Trend is your friend - until the end when it bends

## Data
Area | Notes | Competency area | Core value | Competencies
Recruitment |  | Leadership | Innovation & Strategic ability | Think strategically
Onboarding |  | Leadership | Innovation & Strategic ability | Innovate
Goals |  | Leadership | Innovation & Strategic ability | Champion change
Development | New Areas | Leadership | Customer | Improve systems and processes
Performance | Effectiveness | Leadership | Customer | Commit to quality
Succession | New Areas, Backup - Another focus | Leadership | Customer | Focus on customer needs
Compensation |  | Leadership | Integrity & trust | Lead courageously
|  | Leadership | Integrity & trust | Foster open communication
|  | Leadership | Integrity & trust | Act with integrity
|  | Leadership | Performance | Establish plans
|  | Leadership | Performance | Manage execution
|  | Leadership | Performance | Influence others
|  | Leadership | Performance | Drive for results
|  | Leadership | People & developing subordinates | Foster enthusiasm and teamwork
|  | Leadership | People & developing subordinates | Reward and celebrate teamwork
|  | Leadership | People & developing subordinates | Attract and develop talent
|  | Leadership | People & developing subordinates | Build relationships
|  | Leadership | Personal Effectiveness | Use sound judgment
|  | Leadership | Personal Effectiveness | Convey information
|  | Leadership | Personal Effectiveness | Adapt and develop oneself
|  | Leadership | Personal Effectiveness | Know the organization and the business
|  | Industry | Industry knowledge
|  | Industry | Client focus
|  | Industry | Global perspective
|  | Implementation | Flexibility & adaptibility
|  | Implementation | Communication skills
|  | Implementation | Results orientation

## Backlog
Story# | Feature | Priority | Story title | In order to | As a | I should be able to | Acceptance criteria | Local tests (Unit & Local Integration) | Functional tests (Full Integration & E2E) | Sprint# | Status
A001 | cases | M | View my cases | manage my cases | case manager | view all my cases | 1. can view list of own cases alphabetically | LA001-01: should list own cases in card view by default LA001-02: should list cases alphabetically LA001-03: should navigate to case activities when clicked on a case LA001-04: should limit case display name to 20 characters with tooltip and expandable view LA001-05: should reactively add or remove case assignments from list LA001-06: should be able to switch view mode between card view, tabular view or bucket view LA001-07: should allow option to retain last view mode selection | FA001-01: should list own cases FA001-02: should reactively add or remove case assignments from list FA001-03: should retain last view mode selection within a session FA001-003-04: should list selected case activities when clicked on a case
A002 | cases | M | Add a case | track activities of a new case | case manager | add a new case | 1. can add my new cases 2. cannot use invalid names for cases | LA002-01: should show option to "Add new case" LA002-02: should show new form when "Create" button clicked LA002-03: should not accept characters other than alphanumeric and space LA002-04: should not accept less than 5 characters or more than 50 characters LA002-05: should hide/cancel new form when Esc key pressed or cliicked outside new form. LA002-06: should not retain the last value when add cancelled and clicked again | FA002-01: should not accept duplicate case names FA002-02: should add a new case when "Create" button clicked FA003-03: should cancel add action when Esc clicked or clicked outside new form
A003 | cases | M | View my case activities | manage case activities | case manager | view my case activities | 1. can view activities of my case | LA003-01: should list case activities in tabular view by default LA003-02: should list activities based on ascending due date LA003-03: should allow option to retain last sort mode LA003-04: should open activity details pane when clicked on an activity LA001-05: should limit activity display name to 20 characters with tooltip and expandable view LA001-06: should be able to switch view mode between card view, tabular view or bucket view LA001-07: should allow option to retain last view mode selection | FA003-01: should list activities based on ascending due date FA003-02: should retain last sort mode selection within a session
A004 | cases | M | View other cases | manage cases I follow | case manager | view all cases I follow | 1. can view list of followed cases alphabetically | LA004-01: should list followed cases LA004-02: should list cases alphabetically LA004-03: should redirect to "View my case details" when clicked on a case LA004-04: should limit case display name to 20 characters with tooltip and expandable view | FA004-01: should list followed cases FA004-02: should unfollow and remove from list when case assigned to me
A005 | cases | M | View case activity details | view case updates | case manager | view my case activity details | 1. can view case activity details
A006 | cases | M | Follow a case | track other cases of interest | case manager | follow another case | 1. can view list of all other cases alphabetically 2. can follow a case from a list of other cases
A007 | cases | M | Assign a case | share work load | case manager | assign other members to a case | 1. can view list of all users 2. can assign a user to my case 3. cannot assign the same user twice to my case
A008 | Security | M | Sign in to application | perform authorized actions in the application | user | use the application only with secure credentials | 1. can sign in with the correct credentials 2. is directed into the application on successful sign in 3. User's last log in information is displayed after successful attempt 4. cannot sign in with incorrect credentials 5. All successful and failed signin attempts are logged in audit history 6. is shown a warning message on unsuccessful sign in 7. cannot login to locked or inactivated account | LA008-01: should render SignIn
A009 | Security | M | Sign in to mobile application | perform authorized actions when device is offline | mobile user | authenticate locally when the device is offline | 1. can sign in with the correct credentials when the device is offline 2. is not able to signin with incorrect credentials
A010 | Security | M | Strong password criteria | ensure the password is not easy to crack | security conscious user | only provide strong credentials to the application | 1. Password should satisfy minimum requirements 2. Last 5 paswords cannot be reused 3. User's device is registered after two factor authentication 4. User's account is locked after 5 consequtive unsuccessful attempts
A011 | Security | S | Reset password | enable access to the application when password is forgotten | user | reset my password | 1. can request forgotten username or password reset 2. User's identity is verified using two factor authentication 3. Password reset link is timed out within 24 hours
A012 | Security | M | Internal service call authentication | secure access within the application | security conscious user | secure authentication across all internal service calls within the application | 1. Application logs out automatically after 20 minutes of inactivity 2. All service calls should verify identity and authorized access of the user 3. All service calls should log invocation details in audit history 4. Any transmission of credentials should be encrypted 5. Any storage of credentials should be encrypted
A013 | Framework | M | Application layout | perform my functions | user | navigate easily to different screens and views | 1. Application displays a sidebar to navigate across modules 2. Application displays a menus to navigate across features
A014 | Framework | S | Application search | quickly visit other screens and views | user | use shortcuts for navigation | 1. Application allows a search feature to search and navigate to features
A015 | Framework | M | Context header | not have to rely on my memory and reduce possibility of errors or misinterpretation | user | see a quick view of the context information such as study, site, patient etc | 1. Application displays context details in header for the selected context 2. has ability to quickly change context from header
A016 | Framework | S | Breadcrumbs | efficiently perform my actions in the application | user | easily revisit back the screens I visited earlier to check its contents | 1. Application should display attribute based breadcrumbs 2. can click on a breadcrumb link to visit with the current context
A017 | Framework | S | Application logging |  |  | Logging
A018 | Framework | S | Display notifications |  |  | Notifications
A019 | Study Sites | M | List study participants | perform further actions for the selected participant | site team member | see a list of study participants to choose from |  | LA019-01: displays list of participants LA019-02: should display message on no results LA019-03: should display participant details LA019-04: should check for proper gender symbol LA019-05: should display count of results LA019-06: should not display horizontal scrollbar LA019-07: should display issues indicator for the participant LA019-08: should check for proper date formats LA019-09: should display total issues indicator for a participant LA019-10: should display pending enrollment date for pending enrollments LA019-11: should display loading symbol when results being fetched LA019-12: should lazy load more results on scrolling
A020 | Study Sites | M | Sort study participants listing | quickly narrow down to the participant of interest | site team member | sort the list of participants |  | LA020-01: should sort on selected criteria LA020-02: should apply selected sorting when filtering
A021 | Study Sites | M | Filter study participants listing | quickly narrow down to the participant of interest | site team member | filter the list of participants based on SPID |  | LA021-01: should filter on selected criteria LA021-02: should apply selected filtering when sorting LA021-03: should not allow invalid characters or values on filter LA021-04: show blocking message on search with no filter LA021-05: should refresh results on cancelling filter
A022 | Study Sites | M | Navigate to encounter from study participant listing | view or edit the information captured during the encounter | site team member | visit the encounter details of a selected participant |  | LA022-01: should allow to visit existing scheduled encounter for a participant LA022-02: should allow to visit existing unscheduled encounter
A023 | Enrollment | M | Register participant and create screening encounter | the participant can be screened for eligibility and subsequently enrolled for the study at the site | site team member | register a potential participant to perform screening |  | LA023-01: should allow to enroll a new participant LA023-02: should allow to create new unscheduled encounter for a participant LA023-03: should allow to create new scheduled encounter for a participant
A024 | Enrollment | M | Order lab tests | I can match the results to screening criteria | site investigating physician | order lab tests | 1. should have the ability to create, eidt or delete a lab test order 2. should have the ability to view list of test orders 3. should have option to pick labs from a dictionary list of tests. should be able to search the test based on wildcard search of test name from an autocomplete list.
A025 | Framework | M | Database and service scripts for lab tests |  | application developer | store and retrieve using a database and API services - lab results | 1. Create remote and local tables and scripts 2. Update DB model with comments 3. Create sample data and scripts 4. Create basic save and retrieval stored procedures and scripts 5. Create remote API web service & unit tests 6. Create UI / Angular data access object / service & unit tests
A026 | Enrollment | M | Add or edit lab tests | the information can be used for evaluation of the patient | site team member | add or edit the lab test results | 1. Screen displays lab tests specific to the encounter for the study selected 2. is able to add, edit or clear lab results 3. Screen defaults the test date to the encounter date. has the option to change the date to the actual test date 4. has option to add multiple results for same test on an encounter with different date times 5. Screen displays standard unit (application configured) of the test result. has option to change unit 6. Screen displays read-only standard normal ranges (application configured) for the test result. 7. has ability to identify a test result as a critical value
A027 | Enrollment | M | Lab tests additional validations | relevant results can be added productively | site team member | preconfigure settings for appropriate display of lab results | 1. Screen provides ability for skip patterns and conditional rendering of tests based on other test result values or context (gender, age etc)
A028 | Enrollment | M | Enroll participant |  | site team member | confirm the eligibility of the participant and enroll him or her into the study
A029 | Enrollment | M | Deny enrollment |  | site team member | confirm the ineligibility of the participant and decline his or her participation in the study
A030 | Enrollment | M | Edit patient registration or update screening encounter | correct any errors, complete any missing information and keep the patient record accurate | site team member | update screening encounter information
A031 | Encounters | M | Visit other encounter screens | complete the additional encounter information | site team member | add or edit additional details after participant registration | 1. should be displayed a menu to navigate across different forms of the encounter, once the encounter is recorded 2. should be able to hide or make this menu compact
A032 | Encounters | M | Add custom steps to encounters | I am able to capture any study unplanned information | site team member | add or edit additional steps to encounters | 1. should have the option to choose and add new unscheduled steps / forms on the encounter, and visit these step forms to record information, in case of scheduled or unscheduled encounters
A033 | Encounters | M | Create treatment encounters | additional information can be collected and recorded for that encounter with the patient | site team member | record the encounter information for a patient | 1. should be able to record the encounter date and type of encounter. The encounter date will default to current date. 2. should be able to reconsent the patient if required and view consent history. The patient consent date and consent version will prepopulate from enrollment. 3. In case of unscheduled visit, should record reason for visit 4. should be able to record the patient vitals at the time 5. In case of scheduled study visit, should be able to visit other forms to record additional visit information after this step 6. The encounter date, encounter type, patient consent date and consent version should be available to save the encounter. 7. should be able to save with all other empty values. For every invalid value, an issue shall be recorded. Upon valid value, any previous issue shall be cleared. 8. The system shall notify the user of successful save or error. A persistent icon on the screen will indicate presence of any issues. Clicking the icon will display all issue messages in respective fields. Clicking again will close the respective field messages.
A034 | Framework | M | Database and service scripts for treatment encounters | store the relevant information from the forms and retrieve for reports and exports | application developer | store and retrieve using a database and API services - patient vitals and encounters | 1. Create remote and local tables and scripts 2. Update DB model with comments 3. Create sample data and scripts 4. Create basic save and retrieval stored procedures and scripts 5. Create remote API web service & unit tests 6. Create UI / Angular data access object / service & unit tests
A035 | Framework | M | Database and service scripts for static encounter information tables | store the relevant information from the forms and retrieve for reports and exports | application developer | store and retrieve using a database and API services - patient demographics, co-morbidities, medication history, procedure history, physical exam, med orders and referrals | 1. Create remote and local tables and scripts 2. Update DB model with comments 3. Create sample data and scripts 4. Create basic save and retrieval stored procedures and scripts 5. Create remote API web service & unit tests 6. Create UI / Angular data access object / service & unit tests
A036 | Framework | M | Database and service scripts for dynamic encounter information tables | store the relevant information from the forms and retrieve for reports and exports | application deveboper | store and retrieve using a database and API services - dynamic form elements for eligibility, disease characteristics, social factors, risk factors, HepC history, review of systems, clinical impressions, treatment response, and discharge instructions | 1. Create remote and local tables and scripts 2. Update DB model with comments 3. Create sample data and scripts 4. Create basic save and retrieval stored procedures and scripts 5. Create remote API web service & unit tests 6. Create UI / Angular data access object / service & unit tests
A037 | Framework | M | Database and service scripts for summary and issue resolution tables | store the relevant information from the forms and retrieve for reports and exports | application developer | store and retrieve using a database and API services - encounter step summary and issue resolution information | 1. Create remote and local tables and scripts 2. Update DB model with comments 3. Create sample data and scripts 4. Create basic save and retrieval stored procedures and scripts 5. Create remote API web service & unit tests 6. Create UI / Angular data access object / service & unit tests
A038 | Enrollment | M | Add or edit patient eligibility | check criteria for eligibility during enrollment | site team member | be able to add or edit for the selected patient - patient eligibility | 1. should be able to save with atleast one nonempty values. For every invalid field value, an issue shall be recorded. Upon valid value, any previous issue for the field shall be cleared. 2. The system shall notify the user of successful save or error. A persistent icon on the screen will indicate presence of any issues. Clicking the icon will display all issue messages in respective fields. Clicking again will close the respective field messages.
A039 | Encounters | M | Add or edit patient demographics | capture and report on patient demographics during the treatment research | site team member | be able to add or edit for the selected patient - patient demographics | 1. should be able to save with atleast one nonempty values. For every invalid field value, an issue shall be recorded. Upon valid value, any previous issue for the field shall be cleared. 2. The system shall populate the current gender and date of birth from Screening information. Any update to these values should be reflected in screening and patient information. 3. The system shall notify the user of successful save or error. A persistent icon on the screen will indicate presence of any issues. Clicking the icon will display all issue messages in respective fields. Clicking again will close the respective field messages.
A040 | Encounters | M | Add or edit patient disease characteristics | capture and report on patient disease characteristics during the treatment research | site team member | be able to add or edit for the selected patient - patient disease characteristics | 1. should be able to save with atleast one nonempty values. For every invalid field value, an issue shall be recorded. Upon valid value, any previous issue for the field shall be cleared. 2. The system shall notify the user of successful save or error. A persistent icon on the screen will indicate presence of any issues. Clicking the icon will display all issue messages in respective fields. Clicking again will close the respective field messages.
A041 | Encounters | M | Add or edit patient Social factors | capture and report on patient social factors during the treatment research | site team member | be able to add or edit for the selected patient - patient social factors | 1. should be able to save with atleast one nonempty values. For every invalid field value, an issue shall be recorded. Upon valid value, any previous issue for the field shall be cleared. 2. The system shall notify the user of successful save or error. A persistent icon on the screen will indicate presence of any issues. Clicking the icon will display all issue messages in respective fields. Clicking again will close the respective field messages.
A042 | Encounters | M | Add or edit patient Risk factors | capture and report on patient risk factors during the treatment research | site team member | be able to add or edit for the selected patient - patient risk factors | 1. should be able to save with atleast one nonempty values. For every invalid field value, an issue shall be recorded. Upon valid value, any previous issue for the field shall be cleared. 2. The system shall notify the user of successful save or error. A persistent icon on the screen will indicate presence of any issues. Clicking the icon will display all issue messages in respective fields. Clicking again will close the respective field messages.
A043 | Encounters | M | Add or edit patient Hep C History | capture and report on patient Hep C History during the treatment research | site team member | be able to add or edit for the selected patient - patient Hep C History | 1. should be able to save with atleast one nonempty values. For every invalid field value, an issue shall be recorded. Upon valid value, any previous issue for the field shall be cleared. 2. The system shall notify the user of successful save or error. A persistent icon on the screen will indicate presence of any issues. Clicking the icon will display all issue messages in respective fields. Clicking again will close the respective field messages.
A044 | Encounters | M | Add or edit patient Co-morbidities | capture and report on patient co-morbidities during the treatment research | site team member | be able to add or edit for the selected patient - patient co-morbidities | 1. should be able to save with atleast one nonempty values. For every invalid field value, an issue shall be recorded. Upon valid value, any previous issue for the field shall be cleared. 2. The system shall notify the user of successful save or error. A persistent icon on the screen will indicate presence of any issues. Clicking the icon will display all issue messages in respective fields. Clicking again will close the respective field messages.
A045 | Encounters | M | Add or edit patient Medication history | capture and report on patient medication history during the treatment research | site team member | be able to add or edit for the selected patient - patient medication history | 1. should be able to save with atleast one nonempty values. For every invalid field value, an issue shall be recorded. Upon valid value, any previous issue for the field shall be cleared. 2. The system shall notify the user of successful save or error. A persistent icon on the screen will indicate presence of any issues. Clicking the icon will display all issue messages in respective fields. Clicking again will close the respective field messages.
A046 | Encounters | M | Add or edit patient Procedure history | capture and report on patient procedure history during the treatment research | site team member | be able to add or edit for the selected patient - patient procedure history | 1. should be able to save with atleast one nonempty values. For every invalid field value, an issue shall be recorded. Upon valid value, any previous issue for the field shall be cleared. 2. The system shall notify the user of successful save or error. A persistent icon on the screen will indicate presence of any issues. Clicking the icon will display all issue messages in respective fields. Clicking again will close the respective field messages.
A047 | Encounters | M | Add or edit patient Review of systems | capture and report on patient review of systems during the treatment research | site team member | be able to add or edit for the selected patient - patient review of systems | 1. should be able to save with atleast one nonempty values. For every invalid field value, an issue shall be recorded. Upon valid value, any previous issue for the field shall be cleared. 2. The system shall notify the user of successful save or error. A persistent icon on the screen will indicate presence of any issues. Clicking the icon will display all issue messages in respective fields. Clicking again will close the respective field messages.
A048 | Encounters | M | Add or edit patient Clinical Impression | capture and report on patient clinical impression during the treatment research | site team member | be able to add or edit for the selected patient - patient clinical impression | 1. should be able to save with atleast one nonempty values. For every invalid field value, an issue shall be recorded. Upon valid value, any previous issue for the field shall be cleared. 2. The system shall notify the user of successful save or error. A persistent icon on the screen will indicate presence of any issues. Clicking the icon will display all issue messages in respective fields. Clicking again will close the respective field messages.
A049 | Encounters | M | Add or edit patient Vitals | capture and report on patient vitals during the treatment research | site team member | be able to add or edit for the selected patient - patient vitals | 1. should be able to save with atleast one nonempty values. For every invalid field value, an issue shall be recorded. Upon valid value, any previous issue for the field shall be cleared. 2. The system shall notify the user of successful save or error. A persistent icon on the screen will indicate presence of any issues. Clicking the icon will display all issue messages in respective fields. Clicking again will close the respective field messages.
A050 | Encounters | M | Add or edit patient Physical Exam | capture and report on patient physical exam during the treatment research | site team member | be able to add or edit for the selected patient - patient physical exam | 1. should be able to save with atleast one nonempty values. For every invalid field value, an issue shall be recorded. Upon valid value, any previous issue for the field shall be cleared. 2. The system shall notify the user of successful save or error. A persistent icon on the screen will indicate presence of any issues. Clicking the icon will display all issue messages in respective fields. Clicking again will close the respective field messages.
A051 | Encounters | M | Add or edit patient Orders | capture and report on patient orders during the treatment research | site team member | be able to add or edit for the selected patient - patient orders | 1. should be able to save with atleast one nonempty values. For every invalid field value, an issue shall be recorded. Upon valid value, any previous issue for the field shall be cleared. 2. The system shall notify the user of successful save or error. A persistent icon on the screen will indicate presence of any issues. Clicking the icon will display all issue messages in respective fields. Clicking again will close the respective field messages.
A052 | Encounters | M | Add or edit patient Discharge Instruction | capture and report on patient discharge instruction during the treatment research | site team member | be able to add or edit for the selected patient - patient discharge instruction | 1. should be able to save with atleast one nonempty values. For every invalid field value, an issue shall be recorded. Upon valid value, any previous issue for the field shall be cleared. 2. The system shall notify the user of successful save or error. A persistent icon on the screen will indicate presence of any issues. Clicking the icon will display all issue messages in respective fields. Clicking again will close the respective field messages.
Note on J1: Vivek Pillai: Integration test cases across user stories are defined at the terminating user stories